## Slide 1
Name of Project In-charge: Dr. Raza Ullah Khan
Name of the Project | Productivity Enhancement of Wheat | 
Location/Component | LRRI, NARC | 
Original Cost : | 30,455.353 million Federal share = 5632.774 million (18.50%) Provincial share = 12526.591 million (41.13%) Farmers’ share = 12295.985 million (40.37%) | 
Source of Funding | PSDP + ADP + Farmers | 
Approved by | CDWP (06-05-2019) , ECNEC (29-08-2019) | 
Project Duration | 5 YEARS: (2019-20 to 2023-24) | 
Actual Date of Commencement: 23.09.2019 | 23.09.2019 Completion Date; 30.06.2024 | Completion Date: 30.06.2024
Financial Progress | 100% | 
Physical Progress | 200% | 

## Slide 2
Physical Progress
Continued….
Activity | Progress-2019-20 |  |  |  | 
 | Unit | Targets | Revised targets (If any) | Achieve. | Reason for not achieving targets
Demonstrations Field Trials | Nos. | 10 | - | 16 | -
Nutrients Indexing Survey | Nos. | 01 | - | 01 | -
Farmer Field Days | Nos. | 01 | - | 00 | Due to Covid’19
Lab. Upgradation | Nos. | 02 | - | 02 | -
Capacity Building | Nos. | 10 | - | 10 | -
Procurement of Lab. Instruments | Nos. | 08 | - | 08 | -
Procurement of Office equipment | Nos. | 06 | - | 06 | -

## Slide 3
Physical Progress
Continued….
Activity | Progress-2020-21 |  |  |  | 
 | Unit | Targets | Revised targets (If any) | Achieve. | Reason for not achieving targets
Demonstrations Field Trials | Nos. | 10 | - | 15 | -
Nutrients Indexing Survey | Nos. | 01 | - | 01 | -
Farmer Field Days | Nos. | 01 | - | 00 | Due to Covid’19
Capacity Building | Nos. | - | - | 10 | -
Lab. Upgradation | Nos. | 01 | - | 01 | -

## Slide 4
Physical Progress
Continued….
Activity | Progress-2021-22 |  |  |  | 
 | Unit | Targets | Revised targets (If any) | Achieve. | Reason for not achieving targets
Demonstrations Field Trials | Nos. | 10 | - | 14 | -
Nutrients Indexing Survey | Nos. | 01 | - | 01 | -
Farmer Field Days | Nos. | 02 | - | 02 | -
Capacity Building | Nos. | - | - | 20 | -
Lab Upgradation | Nos. | 01 | - | 01 | -

## Slide 5
Physical Progress
Continued….
Activity | Progress-2022-23 |  |  |  | 
 | Unit | Targets | Revised targets (If any) | Achieve. | Reason for not achieving targets
Demonstrations Field Trials | Nos. | 10 | - | 15 | -
Nutrients Indexing Survey | Nos. | 01 | - | 01 | -
Farmer Field Days | Nos. | 02 | - | 00 | Unavailability of Funds
Capacity Building | Nos. | - | - | 20 | -

## Slide 6
Activity | Unit | Targets | Revised targets (If any) | Achieve. | Reason for not achieving targets
Demonstrations Field Trials | Nos. | 40 |  | 60 | -
Nutrients Indexing Survey | Nos. | 04 | - | 04 | -
Farmer Field Days | Nos. | 04 | - | 02 | - Covid’19 Issue - Lack of Funds
Lab. Upgradation | Nos. | 04 | - | 04 | -
Capacity Building | Nos. | - | - | 60 | -
Procurement of Lab. Instruments | Nos. | 08 | - | 08 | -
Procurement of Office equipment | Nos. | 06 | - | 06 | -
Cumulative Physical Progress-2019-20 to 2022-23
Continued….

## Slide 7
Activity | Unit | Targets
Demonstrations Field Trials | Nos. | 15
Nutrients Indexing Survey | Nos. | 01
Farmer Field Days | Nos. | 01
Capacity Building | Nos. | 10
Plan For 2023-24

## Slide 8
Years | PC-I Allocation |  |  | Actual Allocation |  |  | Actual Release |  |  | Expenditure |  | 
 | PSDP | ADP | Total | PSDP | ADP | Total | PSDP | ADP | Total | PSDP | ADP | Total
2019-20 | 15.235 |  | 15.235 | 11.000 |  | 11.000 | 6.000 |  | 6.000 | 6.000 |  | 6.000
2020-21 | 35.085 |  | 35.085 | 10.120 |  | 10.120 | 10.120 |  | 10.120 | 10.120 |  | 6.880
2021-22 | 11.070 |  | 11.070 | 9.664 |  | 9.664 | 6.880 |  | 6.880 | 6.880 |  | 6.880
2022-23 | 10.215 |  | 10.215 | 10.090 |  | 10.090 | 8.415 |  | 8.415 | 8.415 |  | 8.415
2023-24 | 10.530 |  | 10.530 | 7.000 |  | 7.000 | 0.500 |  | 0.500 | 0.500 |  | 0.500
Total | 82.135 |  | 82.135 | 47.874 |  | 47.871 | 31.915 |  | 31.915 | 31.915 |  | 31.915
Financial Progress
In Millions

## Slide 9
Bottle Neck and Proposals
Bottle Neck
Lack of Funds
Proposals

## Slide 10
THANKS